## Slide 1
City of Newark
Affordable Housing Work Plan
May 13, 2021
Steven Turner, Community Development Director
Paul Peninger, Baird and Driskell Community Planning
Notes: AG

## Slide 2
Background: Housing Element
Housing Element of the General Plan
Updated and adopted in 2015 for the 2015-2023 “fifth cycle” planning period
Sets forth goals, policies, programs, and actions for addressing the community’s housing needs across income levels and household types
Newark will soon begin the process of updating the Housing Element for the 2023-2031 “sixth cycle” planning period
Notes: AG

## Slide 3
Background: RHNA
2015-2023 Housing Element, containing the “fifth cycle” Regional Housing Needs Assessment (RHNA)
Income Category | RHNA units | Production 2015-2020
Very-low Income (up to 50% AMI) | 330 | 0
Low-Income (51-80% AMI) | 167 | 0
Moderate Income (81-120% AMI) | 158 | 36
Above Moderate Income (greater than 120%) | 423 | 1,062
Total | 1,078 | 1,098
Source: City of Newark 2020 Annual Progress Report
Notes: AG

## Slide 4
Background: RHNA
2023-2031 Housing Element, containing the “sixth cycle” Regional Housing Needs Assessment
Income Category | RHNA units
Very-low Income (up to 50% AMI) | 464
Low-Income (51-80% AMI) | 268
Moderate Income (81-120% AMI) | 318
Above Moderate Income (greater than 120%) | 824
Total | 1,874
Notes: AG

## Slide 5
Background
Housing Impact Fee
  Intended to mitigate housing impacts as a result of development
  $21.52 per sqft for the first 1,000 sqft, $8.62 per sqft >1,000 square feet
  Payment due prior to issuance of building permits
  As of May 2021- Approximately $31M collected
Notes: AG

## Slide 6
City of Newark
Affordable Housing Work Plan
Paul Peninger, Baird and Driskell Community Planning
Notes: AG

## Slide 7
Affordable Housing Workplan
Key Stakeholder Interviews
Key Priorities
DRAFT Workplan
Timing and Budget
Notes: AG

## Slide 8
Key Stakeholder Interviews
Notes: AG

## Slide 9
Priority Housing Needs
“Newark needs Housing for all segments of the community”
Young families
Key workers (teachers, first responders, etc.)
People and families at risk of homelessness
People with disabilities and other special housing needs
Low-income Seniors
Notes: AG

## Slide 10
Priority Housing Types
“We need all types of housing, but in the right places”
Rental Apartments (medium- to high-density in select areas)
Condominiums and townhomes (including for first-time homebuyers)
Missing middle housing types (duplexes, four-plexes, etc).
Notes: AG

## Slide 11
Priority Housing Programs
Design Inclusionary Housing Ordinance
Partner with affordable housing developers to develop affordable rental housing (Issue NOFA)
Acquire sites, potentially with other local organizations
Create affordable homeownership program
Local Preference Ordinance
Notes: AG

## Slide 12
Implementation
Notes: AG

## Slide 13
2021-2022 Priorities
Initiate Housing Element Update Process
Inclusionary Housing Program
  RFP
  Community/stakeholder engagement
  Test policies and incentives
  Implement program
Affordable Housing Developer NOFA and/or sites acquisition program
Affordable Homeownership Program
Local preferences ordinance
Notes: AG

## Slide 14
Affordable Housing Workplan Overall Schedule
1) Workplan (April – May, 2021)
Key stakeholder interviews and draft workplan, April 2021
      Finalize Workplan and Present to Council for approval, May 13, 2021
      2) Housing Element (May 2021 – January 2023)
      Issue RFP for Housing Element Consultant, May 2021
      Interviews and Selection Process, June 2021
      Housing Element Update, Fall 2021- December, 2022
Notes: AG

## Slide 15
Affordable Housing Workplan Overall Schedule
3) Implement Workplan
Inclusionary Housing Feasibility Study and Ordinance, Summer- Fall 2021
Initial Affordable Housing Trust Fund NOFA, Fall 2021
Design Public Sites Development Strategy/RFP Process, Fall-Winter 2021
Local Preferences Ordinance Development, Summer-Fall 2021
Affordable Homeownership Program, Early 2022
Notes: AG

## Slide 16
Detailed Budget and Schedule (pg
Activity | Budget | Schedule | Products
Housing Element | $150K-$200K | 5/21-12/22 | RFP – B+D and City Staff Housing Element Update - Consultant TBD
Update IH Program – Nexus Study and Feasibility Analysis | $75K-$100K | Fall, 2021 | RFP – B+D and City Staff Stakeholder Outreach Strategy –B+D and CITY Staff Final Report and Recommendations – Consultant TBD Updated Ordinance – Consultant, Staff + Attorney
Notes: AG

## Slide 17
Detailed Budget and Schedule (pg
Activity | Budget | Schedule | Products
Affordable Housing NOFA | 40% of Fund balance | Fall, 2021 | Develop and administer NOFA– B+D, City Staff and City Attorney
Sites Acquisition Strategy | 40% of Fund balance | Fall-Winter, 2021 | Develop Strategy – B+D, City Staff and City Attorney
Local Preferences Policy | $50K | Summer-Fall, 2021 | Create and Adopt Policy - B+D, City Staff and City Attorney
Design Affordable Ownership Program | $50K + Annual Budget Allocation, 5% of Fund balance | First Quarter, 2022 | Create and Adopt Program - B+D, City Staff and City Attorney
Notes: AG

## Slide 18
Thank you!
City of Newark
Affordable Housing Work Plan
May 13, 2021
Steven Turner, Community Development Director
Paul Peninger, Baird and Driskell Community Planning
Notes: AG